## Sheet1
High-level Requirements
Project Name:	Order Book
Project Stage:	Build/Unit Test

High-level Requirement ID	Business Topic	Requirement Name	Short Description	Priority	Release Number	Description	Requirement Source	Business/ Process Area	Owner	Date	Stability	Dependencies	Status	Owner	Change Request ID	Is this an Interface Requirement? (Y/N)	Notes
1	Display Orders/transactions	Dynamic Selection	in the index page, show only symbols that are in our database					Service / Controller / FE	Angelica	25/09/23					Y
			delete an order from the order table keeps a copy in our database, for the transaction history					Service	Angelica	20/09/23
			delete an unmatched order from the database					Service	Angelica	20/09/23
			two methods are needed for gettingAllOrders: one to get buyOrders and one for SellOrders					Service/Query	Angelica	20/09/23
2	View Orderbook	Display Buys/Sells	Show both types side by side					Front End	Angelica	20/09/23					Y
3	View Orderbook	Ordering Orders	lowest sell at top, highest ask at top					Front End	Angelica	20/09/23					Y
4	View Trade History	DisplayTransaction history	Shows history of all transactions					Front End	Angelica	20/09/23
5	View Trade History	Display Trade history	Shows transaction history for a specific symbol

6	Testing Requirements	Test Get All Orders					Service Tests
7	Testing Requirements	Test Get All Buy Orders					Service Tests
8	Testing Requirements	Test Get All Sell Orders					Service Tests
9	Testing Requirements	Test Get All Transactions					Service Tests
10	Testing Requirements	Test Get All Symbols of Transactions					Service Tests

11	Persist Data	get all order					service	Angelica	20/09/23
12	Persist Data	getl all buy orders					service	Angelica	20/09/23
13	Persist Data	get all sell orders					service	Angelica	20/09/23
14	Persist Data	get all transactions					service	Angelica	20/09/23
15	Persist Data	get all transactions for symbol					service	Angelica

16	Buy Orders					Controller/Service	Angelica	20/09/23
17	Sell Orders					Controller/Service	Angelica	20/09/23
18	Delete Order					Controller/Service	Angelica	20/09/23
19	Match Order					Controller/Service	Angelica	20/09/23

20	UI Feedback	Display messages for actions					Front End
21	UI Feedback	Create and pass messages for actions					Controller/Service
22	PostMapping Create order					Controller/Service	Anouska	22/09/23
23	Get Mapping Update Order					Controller/Service	Anouska	22/09/23
24	Get Mapping Delete Order					Controller/Service	Anouska	22/09/23
25	PostMapping Edit Order					Controller/Service	Anouska	22/09/23
26	Index					Front End	Anouska	25/09/23
27	Home					Front End	Anouska	25/09/23
28	Orderbook					Front End	Angelica	25/09/23
29	Symbol not Found					Front End	Angelica	25/09/23
30	Trade History					Front End	Angelica	25/09/23